## Sheet1
Component | Feature | Estimate (Man/Day)
User services | CRUD for user account | 2
| CRUD for role | 2
| User’s role assignment | 2
| Login | 1
| Reset password | 1
| User list | 1
| Role list | 1
| Permission list | 1
Store service | CRUD for user account | 2
| Store list | 1
Order service | Place order | 3
| Complete order | 3
| Cancel order | 2
| Order list | 1
| Order by status | 2
| Queue list by store | 1
| Process order | 2
Customer Mobile app | Android login page | 3
| IOS login page | 3
| Home page design | 2
| Android home page | 5
| IOS home page | 5
| Place order design | 5
| Android place order | 8
| IOS place order | 8
| My orders design | 2
| Android my orders list | 5
| IOS my orders list | 5
| Cancel order design | 2
| Android cancel order | 3
| IOS cancel order | 3
Store app | Android login page | 3
| IOS login page | 3
| Home page design | 2
| Android home page | 5
| IOS home page | 5
| Processing order design | 2
| Android processing order | 3
| IOS processing order | 3
| Complete order design | 2
| Android complete order | 3
| IOS complete order | 3
| Dev testing | 10.2
Admin Web | User management | 15
| Role management | 15
| Permission management | 15
| Store management | 10
Total development |  | 186.2
Dev test and unit test |  | 55.86
Feature testing |  | 55.86
Infra setup |  | 15
Deployment |  | 5
Total for first release |  | 317.92